## Slide 1: Automating Continuous Planning in SAFe
Darius Foo, Jonah Dela Cruz, Subashree Sekar, Asankhaya Sharma
Veracode

## Slide 2: Agile teams
Notes: Originally designed for small, collocated teams
Used today in large organizations of 20,000+ people
78% of the time with multiple distributed teams

## Slide 3
Notes: Scaled Agile Framework (SAFe)
Most popular (35% of respondents in 14th State of Agile report)
(anything else?)

## Slide 4
Notes: Team level – you know
Program level – similar teams forming a train and working on objectives and dependencies together
5 sprints and 1 IP sprint
Portfolio level – management who decide where investment should go come up with priorities for the train (high level)
In Veracode, each product has its own train
  PMs
  Architects
  Security team
  They meet together and come up with the portfolio level work
Each team in their PI objective (what the ART commits to delivering in one PI) has the objectives added – Security, Architecture work and features
Explain about how security process fits in. How PI objectives contains Purina.

## Slide 5: PI Planning
Meet face-to-face
Align goals
Cross-team dependencies
Match demand to capacity

## Slide 6: Limitations
Visibility across geos
Cross-geo dependencies
Manual digitization

## Slide 7: Continuous Planning
Similar in spirit to CI/CD
Global visibility into a continuously-updated plan
Automate away overhead
Transparency and accessibility

## Slide 8: Sapling
A tool for Continuous Planning
Special support for SAFe PI Planning

## Slide 9: PI Planning workflow
Teams begin with a prioritized list of epics
Time is divided into sprints
Epics are divided into user stories and assigned to sprints
Stories are assigned story points
Sprint capacities should be respected

## Slide 10: Story dependencies
Within teams
  e.g. “Research” item should always precede an “Implementation” item
Across teams
  e.g. platform team should finish API before frontend team uses it
  Requires communication
PI Planning is all about surfacing and negotiating cross-team dependencies

## Slide 11: Enabling Continuous Planning
Sapling supports the workflow, allowing users to edit stories, sprints, epics, and boards
Stories are assigned to sprints automatically, so the plan is always up to date
Teams can request to add stories to each other’s boards
Dependencies across the entire organization are always visible
JIRA export

## Slide 12: Story Assignments
Hard constraints:
  Sprint capacity
  Dependencies
Soft constraints (optimization)
  Epic priority: minimize stories in lower-priority epics before higher ones
  Context: minimize distance between dependent stories
  Parallelism: maximize number of people working at the same time
  Conservativeness: maximize earlier sprint assignments over later ones

## Slide 13: Story Requests
Structures the process of negotiating dependencies

## Slide 14: Story Requests
Visualization of cross-team dependencies

## Slide 15: Demo

## Slide 16: Future work
Explainability and UX of solver decisions
Previews
Incremental solving (allowing non-optimal solutions)
Deeper JIRA integration
https://github.com/srcclr/sapling